{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["必须实现","实现界面可不访问后台","暂时不考虑","开发注意事项-前端","后端注意"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"必须实现","index":0,"n_rows":20,"n_cols":9,"rows_kept":20,"merged":[[2,5,3,5]],"flags":["formulas_cached_only"]}
["一期以实现基本功能为主，便利性的功能可暂时不实现。如导入导出暂时可不做"]
["功能","菜单位置","优先级（数字越小优先级越高）","说明",null,"预估","进度","负责人","备注"]
["用户登录/退出",null,1,null,null,1,"已完成",1]
["整体页面布局",null,1,"菜单是动态的",null,null,"已完成",1]
["工作台（首页）","工作台",1,"用户定制化工作台展示",null,1.5,null,1]
["工位","主数据-机器-工位",1,null,null,1,"进行中70%",2]
["采集分析","采集分析",1,"“采集分析”菜单下全部功能",null,5,null,2,"/mdc"]
["班制日历","主数据-时间-班制日历",2,"\"关联工位\"功能可稍后实现",null,1,"进行中",2,"休息日已完成 班制日历待定"]
["员工-岗位-部门","主数据-人员-员工-岗位-部门",2,"导入导出可暂时不做",null,1,"进行中",1]
["数字看板","数字看板",2,"链接到积木报表",null,null,"已完成",2]
["字典管理","配置中心-字典管理",2,null,null,0.5,"已完成",1]
["菜单管理","配置中心-菜单管理",2,null,null,0.5,"已完成",1]
["可视化配置","配置中心-可视化配置",3,null,null,3,"进行中",2,"分类维护已完成"]
["账号权限","配置中心-账号权限",3,"只做“账号”，\"角色\"2个功能",null,0.5,"已完成",1]
["任务调度","配置中心-任务调度",3,"链接调度系统",null,0.5,"已完成",1]
["字典管理","配置中心-字典管理",3,null,null,0.5,"重复",2]
["日志","配置中心-日志",3,null,null,0.5,"已完成",1]
["工位采集模板","主数据-机器-工位采集模板",3,null,null,0.5,"已完成",2]
["运维管理","配置中心-运维管理",3,"目前只做文件存储、应用设置2项",null,0.5,"已完成",1]
["系统外观切换",null,4,"是否实现需要讨论，简单的话预留接口，目前仅实现一套外观即可",null,null,"已完成",1]

{"sheet":"实现界面可不访问后台","index":1,"n_rows":6,"n_cols":4,"rows_kept":6,"flags":["formulas_cached_only"]}
["一期以实现基本功能为主，便利性的功能可暂时不实现。如导入导出暂时可不做"]
["功能","菜单位置","说明"]
["用户登录",null,null,"这个第一个 页签有"]
["机器管理数据","主数据-机器-机器管理数据",null,1]
["生产工艺",null,"此功能需要仔细讨论需求，不一定按照目前功能实现",5]
["参数管理","配置中心-参数管理",null,0.5]

{"sheet":"暂时不考虑","index":2,"n_rows":18,"n_cols":3,"rows_kept":18,"flags":["formulas_cached_only"]}
["功能","菜单位置","说明"]
["物料信息","主数据-物料-物料信息"]
["物料存放","主数据-物料-物料存放"]
["休息日","主数据-时间-休息日"]
["工装","主数据"]
["仓储","主数据"]
["产品工艺","主数据"]
["其他","主数据"]
["多语言","配置中心-多语言"]
["自定义配置","配置中心-自定义配置"]
["多语言","配置中心-多语言"]
["通知","配置中心-通知","通知下所有模块"]
["企业LOGO","企业LOGO"]
["消息通知",null,"点击右上角\"消息通知\"图标"]
["关闭其他/关闭所有",null,"主界面右上角,后期实现"]
["多语言切换（目前为中英）",null,"主界面右上角,后期实现"]
["附件管理","配置中心-附件管理"]
["编码规则管理","配置中心-编码规则管理"]

{"sheet":"开发注意事项-前端","index":3,"n_rows":3,"n_cols":1,"rows_kept":3,"flags":["formulas_cached_only"]}
["原系统内的配置较多，比如语言，字典等，需要先调查原系统加载了什么后端的配置"]
["系统外观如何切换，需要提前考虑"]
["用户认证使用原系统的方式，因为有链接外部应用的菜单，直接链接并传递token了"]

{"sheet":"后端注意","index":4,"n_rows":1,"n_cols":1,"rows_kept":1,"flags":["formulas_cached_only"]}
["分布式文件服务，集成minio？？？配置中心，运维管理：http://192.168.1.199:19000 access key:admin  secret key：admin123  这是什么产品？"]